## Sheet1
|  |  | Sheikh |  | Zafirul |  | Ammar |  | Hadi |  | Habeeb |  | Ajoke
# | Task | Short summary | Todo | Done | Todo | Done | Todo | Done | Todo | Done | Todo | Done | Todo | Done
1 | Requirement Elicitation | All of this task are disscussed and done to gether. 2 Application domain are set | 2021-04-11 | 2021-04-09 | 2021-04-11 | 2021-04-09 | 2021-04-11 | 2021-04-09 | listing 4/11 | 2021-04-09 | 2021-04-11 | 2021-04-09 | 2021-04-11 | 2021-04-09
2 | Requirement Analysis Specification
3 | Requirement Specification |  | 2021-04-12 | 2021-04-11 | 2021-04-12 | 2021-04-11 | 2021-04-12 | 2021-04-11 | 2021-04-12 | 2021-04-11 | 2021-04-12 | 2021-04-11 | 2021-04-12 | 2021-04-11
4 | Requirement Validation | proved by all member | 2021-04-14 | 2021-04-12 | 2021-04-14 | 2021-04-12 | 2021-04-14 | 2021-04-12 | 2021-04-14 | 2021-04-12 | 2021-04-14 | 2021-04-12 | 2021-04-14 | 2021-04-12
5 | meeting leader | make sure the disscusion in the correctpath and the agenda are fullfiled | [5 empty] | for the all meeting
6 | draft requirement diagram | hand drew to make sure that the requirement diagram in the right direction | 2021-04-13 | 2021-04-11 | 2021-04-13 | 2021-04-11 | 2021-04-13 | 2021-04-11 | 2021-04-13 | 2021-04-11 | 2021-04-13 | 2021-04-11 | 2021-04-13 | 2021-04-11
7 | Proper requirement diagram | using online visual paradigm | 2021-04-13 | 2021-04-12 | 2021-04-13 | 2021-04-12
meeting
8 | use case diagram(focus on burning situation) | did by all member by screen sharing. | 2021-04-18 | 2021-04-16 | 2021-04-18 | 2021-04-16 | 2021-04-18 | 2021-04-16 | 2021-04-18 | 2021-04-16 | 2021-04-18 | 2021-04-16 | 2021-04-18 | 2021-04-16
9 | use case diagram(focus on drawning situation)
10 | Sequence diagram (burning situation) | each part are presented to all member to make improvement and to syncronize all diagram | [6 empty] | 2021-04-23 | 2021-04-20
4 | Sequence diagram (drawning situation) | [5 empty] | 2021-04-23 | 2021-04-20
5 | constarint diagram (4/7) |  | 2021-04-23 | 2021-04-20
6 | constraint diagram(3/7) |  |  |  | 2021-04-23 | 2021-04-20
7 | Block diagram (focus on burning situation ) | [9 empty] | 2021-04-23 | 2021-04-20
8 | Block diagram (focus on drawning situaation situation ) | [11 empty] | 2021-04-23 | 2021-04-20
| meeting |  | 2021-04-24
| correct and refine usecase diagram | did by all member by screen sharing. | 2021-04-26 | 2021-04-24 | 2021-04-26 | 2021-04-24 | 2021-04-26 | 2021-04-24 | 2021-04-26 | 2021-04-24 | 2021-04-26 | 2021-04-24 | 2021-04-26 | 2021-04-24
correct and refine block diagram
add subsystem
understand all design patern
| add constraint block to block diagram |  |  | 2021-04-25 |  | 2021-04-25
| meeting |  | 2021-04-26
| refine subsystem | move subsystem | 2021-04-30 |  | 2021-04-30 |  | 2021-04-30 |  | 2021-04-30 |  | 2021-04-30 | 2021-04-26 | 2021-04-30 | 2021-04-26
|  | communication sub system |  |  |  | 2021-04-26
|  | extinguish subsystem | [7 empty] | 2021-04-26
|  | save people subsystem |  | 2021-04-26
|  | notification subsystem | [5 empty] | 2021-04-26
| decide appropriate pattern | decided pattern : Microkernel |  | 2021-04-26 |  | 2021-04-30 |  | 2021-04-26 |  | 2021-04-30 |  | 2021-04-26 |  | 2021-04-30
| refine system architecture | each task did by three persond and need to be presented in the next meeting |  |  |  | 2021-04-26
| refine design idea | [6 empty] | 2021-04-26 |  | 2021-04-26 |  |  |  | 2021-04-26
| meeting |  | 2021-04-30
| refine system pattern |  | 2021-05-06 | 2021-05-06
| refine requirement diagram | [5 empty] | 2021-05-06
| refine use case diagram | [11 empty] | 2021-05-06 | 2021-05-06
| refine contex diagram |  |  |  | 2021-05-06
| refine sequence diagram | [7 empty] | 2021-05-06